## Work Division
Week | Team Members
| Shubham | Rajat | Anirban | Xin Chen | Pavan | Aditya
Week3 | Initial Research & Planning | Initial Research & Planning | Initial Research & Planning | Initial Research & Planning | Initial Research & Planning | Initial Research & Planning
Week4 | User Management - OTP Authentication Handling | User Management - OTP Authentication Handling | Initial UI Design | Initial UI Design | Initial Database Design | Initial Database Design
Week5 | Database to OTP Service Integration | UI Development - Phase 1 | Peer to Peer Research | UI Development - Phase 1 | Peer to Peer Research | Database to OTP Service Integration
Week6 | Distributed Algorithm Implementation Research | UI Development - Phase 1 | Peer to Peer - Phase 1 | Distributed Algorithm Implementation Research | UI Development - Phase 1 | Peer to Peer -Phase 1
Week7 (Reading Week) | Testing - Peer to Peer Phase 1 | Distributed Algorithm Implementation - Phase 1 | Testing - Peer to Peer Phase 1 | UI Development - Phase 2 | Testing - UI Development Phase 1 | UI Development - Phase 2
Week8 | Distributed Algorithm Implementation - Phase 2 | Distributed Algorithm Implementation - Phase 2 | Peer to Peer - Phase 2 | Testing - Distributed Algorithm Implementation Phase 1 / UI Development Phase 2 | Integration Peer to Peer Phase 1 and UI Development Phase 1/2 | Testing - Distributed Algorithm Implementation Phase 1 / UI Development Phase 2
Week9 | Integration Distributed Algorithm Phase 1 and UI Development Phase 1/2 | Testing - Peer to Peer Phase 2 / Distributed Algorithm Implementation Phase 2 | Integration Distributed Algorithm Phase 1 and UI Development Phase 1/2 | UI Development - Phase 3 | Load Balancing and AWS REST Services Deployment | Load Balancing and AWS REST Services Deployment
Week10 | Load Balancing and AWS REST Services Deployment | Distributed Algorithm Implementation - Phase 3 | Integration Peer to Peer Phase 2 and UI Development Phase 3 | Integration Peer to Peer Phase 2 and UI Development Phase 3 | Testing - UI Development Phase 3 | Distributed Algorithm Implementation - Phase 3
Week11 | End to End Integration/Testing | End to End Integration/Testing | End to End Integration/Testing | End to End Integration/Testing | End to End Integration/Testing | End to End Integration/Testing
Week12 | Document Preperation and Demo Presentation | Document Preperation and Demo Presentation | Document Preperation and Demo Presentation | Document Preperation and Demo Presentation | Document Preperation and Demo Presentation | Document Preperation and Demo Presentation
LEGENDS
Front-End
Backend
Servers
Database
Integration
Testing
Research

## Time Estimates
Time Estimates, Time Spent and Impact/Response to the inaccurate estimates
Work | Sub Category | Time Estimated | Actual Time Spent | Impact | Response
UI Design | User Profile Management | Week 4 and Week 5 | Week 4 and Week 5 | N/A | N/A
| Map (Location Search and Navigation) | Week 5 and Week 6 | Week 5, 6 and 7 | Delayed Implementation due to learning and implementing the google map API | User Journey Management started in parallel, while the Google Map API integration problem was solved.
| User Preferences | Week 7, 8 and 9 | Week 8, 9and 10 | Delayed Implementation due to the research and implementation of Google S2 library | User Journey Management started in parallel, while the Google Map API and Google S2 integration problem was solved.
| User Journey Management | Week 7, 8 and 9 | Week 10 and Week 11 | Delayed Implementation due to delayed integration with the Distributed Implementation. | Testing was done in parallel as soon as one service was created for it, as due to the delay the testing time was coinciding with the same.
Database Design | User Table Creation | Week 4 | Week 4 | N/A | N/A
| Backup Database Creation and Maintainence | Week 4 | Week 4 | N/A | N/A
Peer to Peer Development | Peer Discovery | Week 4 | Week 6 | Delayed implementation; spent time in understanding WiFiBroadcastReceiver and WifiP2PMananger functionalities in Android | Tried various approaches and finalized on a workable approach.
| Peer Connection | Week 5 | Week 6 | Delayed implementation due to research on different protocols and establishing connection | Established connection between peers successfully after rigorous research
| Data Exchange between peers | Week 6 | Week 8 | Delayed implementation due to heavy load on Main Thread of the application | Implemented a workable model for data exchange between peers.
| Registration of Service | Week 7 | Week 9 | Delayed implementation due to time spent in understanding how to register services. | Created a unique service for the app users.
| Brodcasting Services | Week 8 | Week 10 | Implementation Delayed | Service was broadcasted successfully.
| Service Discovery | Week 9 | Week 11 | Implementation Delayed | Service was discovered successfully.
Distributed Implementation | KAFKA Cluster and Nodes Development | Week 6 | Week 6 and Week 7 | N/A | N/A
| KAFKA Datastreaming Development | Week 8 | Week 8 and Week 9 | Tried to integrate Ringpop and Hashrings with KAFKA, but unsuccessful due to lack of adequate documentation for transitioning between Java and Golang, also lack of time to experiment further as it was delaying the future integrations and testing. | Implemented partioning and replication in KAFKA, created multi broker and multi clusters as a way around.
| Google S2 Library Development | Week 6 | Week 6 and Week 7 | Google S2 library adequate documentation not available, available in Golang but not in JAVA, delay due to research and implementation of the same in JAVA to ease integration in future. | Implemented Google S2 Library in JAVA as it was still easier to integrate later rather than taking a totally different approach in the form of GeoHashing as the time had already been spent on the research and implementation of Google S2
| Load Balancing of the Servers | Week 9 | Week 10 | Problem with the creation of only one target group for different REST Services. | Created 3 target groups within a load balancer to manage the load of different REST services at a time.
Integration | UI to Database | Continuous | Continuous | Changes in the approach at times due to integration issues with the external API's, libraries and frameworks. | Had to go back and fix the same in completed tasks again, which led to delay in future processes at times.
| Backend with Database | Continuous | Continuous
| Backend with UI | Continuous | Continuous
| Peer to Peer with UI | Continuous | Continuous
Testing | Database | Week 5 | Week 5 | N/A | N/A
| UI Design | Week 7, 8 and 10 | Week 7, 10 and 11 | Delayed Testing of UI Design Phase 2 and 3 due to delayed integration with backend and distributed system implementation | Further Test Case Preperation was done for Peer to Peer, Distributed Algorithms implementation.
| Peer to Peer | Week 7 and Week 9 | Week 10 and Week 11 | Implementation Delayed; Testing time left was less as it was towards the end of the project deadline. | Further Test Case Preperation was done for Peer to Peer, Distributed Algorithms implementation.
| Distributed Implementation | Week 8, 9 and 11 | Week 10 and Week 11 | Delayed Testing due to challenges with implementation of KAFKA, Google S2 Library and integrating it with Database and UI | Parallel Testing and Integration due to coinciding timeframes as a result of previous delays
Server Deployment | REST Services deployment on AWS | Week 9 | Week 9 | N/A | N/A